GOVERNMENT OF ANDHRA PRADESH

ABSTRACT

Price adjustment for Steel, Cement, Bitumen & POL and adoption of Overhead Charges- Orders issued by R&B Department- Adoption in PR & RD Department also –Orders-issued.

-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-=-

PANCHAYATI RAJ & RURAL DEVELOPMENT (Progs-II) DEPARTMENT

G.O.Ms.No.292						Dated.28.07.2006

Read the following

1. G.O Ms. No: 35, TR&B (R.I) Department dated: 28.02.2006

2. G.O Ms. No: 73, TR&B (R.I) Department dated: 24.04.2006

3. From Engineer-in-Chief, PR, Hyd, Lr.No: T1/29042/06,

dt: 21.03.2006 and 25.04.2006.

-000-

O R D E R:

In the reference 1st and 2nd cited read above orders were issued by TR&B(R.1) Department on Price Adjustment for Steel, Cement, Bitumen & POL and adoption of Overhead charges for all  road works and bridge works including ROBs/ RUBs where estimate value is Rs.50.00 lakhs and above and where  time schedule provided is        6 months and above.

2.	In the reference 3rd read above, the Engineer-in-Chief(PR), Hyderabad has stated that the P.R. Department is executing many works costing less than Rs.50.00 lakhs and these works are situated in interior and remote areas. The class of contractors is also not superior and that they are not financially sound. Some of the works are executed through nominated bodies. In all such cases, the executing agencies are leaving the work in the middle of execution. Hence, requested the Government to issue comprehensive orders in the matter duly incorporating some of the points.

3.	Government have examined the matter carefully and hereby accord permission to accept to allow such price adjustment on works with a value of more than Rs.50.00 lakhs and for which the stipulated period to complete the work as per agreement is more than six months, subject to the following conditions:-

- Price Adjustment shall be both for increase and decrease in the prices for the works completed within the original agreement period,

- In addition, the price adjustment shall be for valid extension given for natural calamities duly limiting to the actual period/days lost and for portion of work where work is delayed due to land acquisition/shifting of utilities ( this shall also be limited to actual length affected).

- The price adjustment shall be effective for all ongoing works for which final bills are not paid and all future works.

- The variation clause will be when the variation in rates is more or less than 5% of the rate provided in the technical sanctioned estimate based on which bids are invited or All India Wholesale Price Index as stipulated in the G.O. 1st read above on the date twenty eight days prior to closing date of submission of bids, which ever is advantageous to the department.

- For works taken up under Externally Aided Projects, the guidelines specified thereon are to be followed.

4.	The Engineer-in-Chief (PR), Hyderabad shall take necessary action in the matter.

5.	This order issues with the concurrence of the Finance Department vide their U.O.Note No.6337/263/A1/Expr.PR&RD/2006, dt: 27.07.2006.

(BY ORDER AND IN THE NAME OF THE GOVERNOR OF ANDHRA PRADESH)

M.SAMUEL

PRINCIPAL SECRETARY TO GOVERNMENT

To

The Engineer-in-Chief(PR), Hyderabad.

Copy to:

The Accounts General, AP, Hyderabad.

The P.S. to M(PR).

The Finance (Expr.PR&RD) Department.

The TR&B(R.I) Department.

/// f.b.o. ///

Sd/-x x x x

SECTION OFFICER

GOVERNMENT OF ANDHRA PRADESH

Office of the Engineer-in-Chief, PR, Hyderabad.

Endt. No. T1/29042/96, dated.01.08.2006

“Communicated”

Sd/- B.Rajeswara Rao

Engineer-in-chief, PR, Hyd

To:

All the Chief Engineers of this Department.

All Superintending Engineers, PR, RWS &  RWS(P) in the State.

All the Executive Engineers, PR, RWS &  RWS(P) in the State.

Copy to SC/SF.

/// t. c . f . b. o ///

Dy. Executive Engineer(T)